Risk Management Report

Project: Automated Micro Story Generator

Team members: Druv Sharma, Durga Sai Sandeep, Isit Pokharel, Tan Nguyen

Reporting Period: November 15, 2025 – February 17, 2026

1. Risk Management Approach

Risk management was treated as a continuous activity throughout the semester. Each week, the team:

- Re-evaluated existing risks

- Updated probability and impact values

- Identified new risks as the project evolved

- Retired risks that were no longer relevant

Risks were prioritized using the following qualitative scale:

| Level | Probability | Impact |
| --- | --- | --- |
| Low | Unlikely, minimal disruption | Minor delay or inconvenience |
| Medium | Possible | Noticeable schedule or quality impact |
| High | Likely | Major functionality, schedule, or grading risk |

2. Initial Risk Identification (Week 1 – Nov 15–21)

At project start, four primary risks were identified based on scope, tools, and team structure described in the proposal.

| Risk ID | Description | Probability | Impact | Priority |
| --- | --- | --- | --- | --- |
| R1 | Team members have uneven experience with Python and version control | Medium | High | High |
| R2 | Template-based story logic may produce repetitive or incorrect output | Medium | Medium | Medium |
| R3 | Schedule risk due to coordination among 4 team members | Medium | High | High |
| R4 | Scope creep from Version 2 AI/image features | Low | High | Medium |

3. Weekly Risk Tracking and Updates

Week 2–3 (Nov 22 – Dec 5):

- Git repository established

- Version 1 design finalized

Updates:

- R1 probability reduced due to peer support

- R3 remains high due to early coordination challenges

Week 4–5 (Dec 6 – Dec 19):

- Core template engine implemented

- Basic UI prototype built

New Risk Identified

| Risk ID | Description | Probability | Impact | Priority |
| --- | --- | --- | --- | --- |
| R5 | Poor input validation causes runtime errors | Medium | Medium | Medium |

Week 6 (Dec 20 – Jan 2):

- End-of-year slowdown

Updates:

- R3 probability increased (holiday scheduling)

- R2 mitigated via expanded templates

Week 7–8 (Jan 3 – Jan 16):

- Version 1 testing underway

- Error handling improved

Risk Retirement:

- R5 retired: Input validation stabilized and tested

Week 9–10 (Jan 17 – Jan 30):

- Version 2 planning (AI/image option discussion)

New Risk Identified

| Risk ID | Description | Probability | Impact | Priority |
| --- | --- | --- | --- | --- |
| R6 | External AI or image library dependency instability | Medium | High | High |

Week 11–12 (Jan 31 – Feb 13):

- Version 2 implementation (chosen option)

- System testing ongoing

Updates:

- R6 mitigated via fallback logic

- R4 probability increases as features expand

Final Week (Feb 14 – Feb 17):

- Final testing and documentation

- Instructor-ready submission

Risk Retirement:

- R1 retired: Team skill gap resolved

- R3 retired: Schedule stabilized

4. Final Risk Register (End of Semester)

| Risk ID | Status | Notes |
| --- | --- | --- |
| R1 | Retired | Team skill alignment achieved |
| R2 | Low | Managed with expanded templates |
| R3 | Retired | Scheduling stabilized |
| R4 | Medium | Controlled by limiting Version 2 scope |
| R5 | Retired | Fully resolved |
| R6 | Low | Mitigated via fallback mechanisms |

5. Risk Management Summary

Throughout the semester, our team made it a priority to monitor and manage project risks by holding weekly reviews and making necessary adjustments. At the beginning, we faced challenges with team skill levels and coordination, but we addressed these issues by working closely together, using version control, and breaking the work into smaller, manageable pieces. When we started adding more advanced features like AI and image processing, we managed the new risks by narrowing the project's scope and putting safeguards in place to keep the system stable.

By following this ongoing risk management process, we were able to meet the goals for both Version 1 and Version 2 of the project. This approach helped us keep the system stable, stay on schedule, and deliver a finished project that matched what we set out to do in the proposal.